60-Day Agentic AI Roadmap + GitHub Daily Documentation Plan

Goal: Learn practical Agentic AI in 60 days at ~1.5 hours/day, while maintaining a visible GitHub learning trail and finishing with a portfolio-ready capstone.

# Daily 1.5-Hour Routine

30 min: learn • 40 min: code • 15 min: experiment/project • 5 min: commit + daily log

Rule: every day should produce a meaningful artifact—code, notes, diagram, experiment, test, metric, or project feature. Never commit secrets/API keys.

# Recommended Repository Structure

README.md — roadmap, progress and project links

00-roadmap/ — 60-day checklist

01-llm-foundations/

02-reliability-evals/

03-tool-calling-agents/

04-rag/

05-open-source-models/

06-finetuning/

07-multi-agent/

08-mcp/

09-capstone/

daily-log/ — day-01.md ... day-60.md

assets/ — diagrams, screenshots and evaluation charts

# 60-Day Plan

| Day | Topic | Learn | Build | GitHub artifact |
| --- | --- | --- | --- | --- |
| 1 | Agentic AI overview | LLM vs workflow vs agent; agent components and loop. | Draw basic agent architecture. | daily-log/day-01.md + diagram |
| 2 | LLM/API basics | Messages, system/user roles, parameters, tokens, context. | Build minimal Python LLM call. | day-02.md + llm_call.py |
| 3 | Tokens & context | Tokenization, context windows, input/output cost. | Run token-count experiments. | day-03.md + token_experiment.py |
| 4 | Prompt engineering | Roles, constraints, examples, output formats. | Compare 3 prompt versions. | day-04.md + prompts.md |
| 5 | Structured outputs | JSON/schema outputs and failure cases. | Build structured extraction. | day-05.md + structured_output.py |
| 6 | Pydantic validation | Schemas and validation errors. | Validate model output. | day-06.md + validator.py |
| 7 | Agent architecture | State, observation, action, termination. | Implement a simple state machine. | day-07.md + architecture.md |
| 8 | Mini Agent I | Simple research/FAQ agent without framework. | Build LLM → response baseline. | day-08.md + mini_agent/ |
| 9 | Reliability | Timeouts, failures, fallbacks. | Add error handling. | day-09.md + reliability.py |
| 10 | Retries & backoff | Retryable errors and exponential backoff. | Build retry wrapper. | day-10.md + retry.py |
| 11 | Idempotency | Duplicate actions and idempotency keys. | Simulate safe refund/payment operation. | day-11.md + idempotency.py |
| 12 | Cost controls | Token budgets, request limits, caching. | Add budget guard. | day-12.md + cost_guard.py |
| 13 | Evaluation basics | Golden cases, test datasets, pass/fail criteria. | Create 20 agent test cases. | day-13.md + eval/cases.json |
| 14 | LLM-as-a-judge | Rubrics, judge prompts and limitations. | Build simple evaluator. | day-14.md + eval/judge.py |
| 15 | Regression testing | Non-determinism and regression tests. | Compare before/after prompt changes. | day-15.md + eval/report.md |
| 16 | Tool calling concepts | Tool schema, arguments, results, model/tool boundary. | Create tool definitions. | day-16.md + tools/ |
| 17 | Tool calling without framework | JSON tool call + execution loop. | Build manual tool loop. | day-17.md + tools/manual_loop.py |
| 18 | Tool descriptions | Schemas, descriptions and validation. | Test weak vs strong descriptions. | day-18.md + tool_description_test.md |
| 19 | Complete agent loop | Observe → decide → act → observe. | Build multi-tool agent with mock tools. | day-19.md + agent_loop/ |
| 20 | Multi-tool routing | Tool selection and routing. | Add 3–4 tools. | day-20.md + router.py |
| 21 | Safety & approval | Approval gates, dry runs, blast radius. | Add human approval to risky tool. | day-21.md + approval_gate.py |
| 22 | Agent memory | Short-term vs long-term memory. | Implement bounded conversation memory. | day-22.md + memory/ |
| 23 | Agent + SQL | Read-only DB tools and SQL safety. | Give agent a SQLite database. | day-23.md + sql_agent/ |
| 24 | Agent debugging | Loops, bad arguments, stale state. | Fix 3 intentional agent bugs. | day-24.md + debugging.md |
| 25 | LangChain | Framework abstractions vs manual implementation. | Rebuild tool agent with LangChain. | day-25.md + langchain_agent/ |
| 26 | LangGraph | State, nodes, edges and routing. | Build graph-based agent. | day-26.md + langgraph_agent/ |
| 27 | Framework comparison | LangChain vs LangGraph vs Agents SDK vs CrewAI. | Create comparison matrix. | day-27.md + framework_comparison.md |
| 28 | Observability | Tracing, latency, tool calls and failures. | Add structured logging. | day-28.md + observability/ |
| 29 | Mini Project II design | Design an agentic research/ops assistant. | Write requirements and tool contracts. | day-29.md + project-2/README.md |
| 30 | Mini Project II build | Core agent, tools and memory. | Working MVP. | day-30.md + project-2/ |
| 31 | Mini Project II reliability | Validation, retries, approval and failure handling. | Create failure tests. | day-31.md + project-2/evals/ |
| 32 | RAG fundamentals | RAG pipeline and when RAG helps. | Build tiny local-text RAG. | day-32.md + rag/basic_rag.py |
| 33 | Embeddings | Semantic embeddings and cosine similarity. | Implement cosine similarity experiment. | day-33.md + embedding_experiment.py |
| 34 | Chunking | Fixed, recursive, semantic chunking and overlap. | Compare chunk sizes. | day-34.md + chunking_experiment.md |
| 35 | Vector databases | Chroma, FAISS, pgvector, metadata. | Store/retrieve embeddings. | day-35.md + vector_store.py |
| 36 | RAG without framework | Retriever → context → LLM. | Build end-to-end RAG manually. | day-36.md + no_framework_rag/ |
| 37 | RAG with LangChain | Loaders, splitters, retrievers and chains. | Rebuild with LangChain. | day-37.md + langchain_rag/ |
| 38 | Conversational RAG | History-aware retrieval and context limits. | Add conversation history. | day-38.md + conversational_rag/ |
| 39 | RAG evaluation | Recall@k, MRR, nDCG, relevance/faithfulness. | Create 30 test cases and calculate metrics. | day-39.md + eval_report.md |
| 40 | Advanced RAG | Reranking, query expansion, metadata filtering. | Add one retrieval improvement. | day-40.md + advanced_rag.md |
| 41 | RAG production | Staleness, permissions, re-indexing, versions. | Design update/re-index strategy. | day-41.md + production_notes.md |
| 42 | Open-source models | Hugging Face models, datasets, spaces. | Run one open model. | day-42.md + open_models/ |
| 43 | Ollama/local inference | Local serving and model selection. | Run a small local model. | day-43.md + local_model.md |
| 44 | Quantization | 16/8/4-bit concepts and tradeoffs. | Run/document a quantization experiment. | day-44.md + quantization.md |
| 45 | Fine-tuning vs RAG | When to prompt, RAG or fine-tune. | Make decision guide with scenarios. | day-45.md + decision_guide.md |
| 46 | Dataset curation | Quality, formatting, splits and leakage. | Create clean instruction dataset. | day-46.md + dataset/ |
| 47 | SFT | Training vs inference and supervised fine-tuning. | Prepare SFT dataset + plan. | day-47.md + sft_plan.md |
| 48 | LoRA | PEFT and adapter concept. | Inspect/build a LoRA setup. | day-48.md + lora_notes.md |
| 49 | QLoRA | 4-bit quantization + LoRA. | Run small experiment if GPU available. | day-49.md + qlora_experiment.md |
| 50 | Multi-agent patterns | Supervisor, specialists, handoffs, parallelism. | Design 3 architectures and tradeoffs. | day-50.md + patterns.md |
| 51 | Multi-agent implementation | Parallel agents, isolated context, aggregation. | Build 3 specialist agents + orchestrator. | day-51.md + basic_team/ |
| 52 | Multi-agent evaluation | Agent/system evaluation, cost and latency. | Test handoff and failure cases. | day-52.md + evals/ |
| 53 | MCP fundamentals | Host, client, server, tools/resources/prompts. | Draw MCP architecture; compare with APIs. | day-53.md + mcp/architecture.md |
| 54 | Build MCP server | FastMCP basics and safe tool exposure. | Build MCP server with 2–3 tools. | day-54.md + mcp/server/ |
| 55 | Agent + MCP | Tool discovery and MCP execution. | Build MCP-enabled agent. | day-55.md + mcp/agent_client/ |
| 56 | Capstone architecture | Combine RAG + tools + agents + MCP. | Write requirements, architecture and eval plan. | day-56.md + capstone/README.md |
| 57 | Capstone build I | Data layer, RAG and core tools. | Working backend skeleton. | day-57.md + capstone/ |
| 58 | Capstone build II | Orchestrator, specialists, MCP and memory. | Working end-to-end prototype. | day-58.md + capstone/ |
| 59 | Capstone evaluation/deploy | Eval suite, logging, errors and deployment. | Metrics, screenshots, demo and fixes. | day-59.md + eval_report.md |
| 60 | Portfolio + interview | Consolidate concepts and explanations. | Polish README and create 50 Agentic AI interview questions. | day-60.md + final README + interview_questions.md |

# Daily Log Template

# Day XX — Topic

## What I learned
- 
- 
- 

## What I implemented
- 

## Key concepts I can explain
1. 
2. 
3. 

## Experiment / Result
- 

## What failed / What I fixed
- 

## Interview takeaway
- 

## Resources
- 

## Commit
`day-XX: <short description>`

# Milestones

Day 15 — LLM fundamentals + reliability + evaluation foundation.

Day 24 — You can build a tool-using agent manually.

Day 31 — First portfolio-worthy agent MVP.

Day 41 — You can build and evaluate production-style RAG.

Day 49 — You understand open-source inference, LoRA and QLoRA.

Day 55 — You can build multi-agent + MCP systems.

Day 60 — One polished capstone + 60-day public learning trail.

# Final GitHub README Should Show

60-day progress checklist

Daily learning log links

Architecture diagrams

Mini projects

RAG evaluation metrics

Agent evaluation results

Failure cases and fixes

Capstone demo/screenshots

Setup instructions

Limitations and future improvements